## Test Cases
id | module | feature | priority | type | precondition | steps | expectedResult | automationScope | owner
TC-AUTH-001 | Authentication | Email login | Critical | Functional | Admin account exists | 1. Go to /login 2. Enter valid email/password 3. Submit form | User is redirected to /dashboard and access token is saved in localStorage. | UI + API | QA
TC-AUTH-002 | Authentication | Invalid login | Critical | Negative | None | 1. Go to /login 2. Enter invalid credentials 3. Submit form | Login fails, error toast appears, user remains on /login. | UI + API | QA
TC-AUTH-003 | Authentication | Public route guard | High | Functional | Valid access_token exists | 1. Open /login directly | PublicRoute redirects authenticated user to /dashboard. | UI | QA
TC-AUTH-004 | Authentication | Private route guard | Critical | Security | No access_token | 1. Open /dashboard directly | PrivateRoute redirects unauthenticated user to /login. | UI | QA
TC-AUTH-005 | Authentication | Google One Tap visibility | Medium | Functional | VITE_GOOGLE_CLIENT_ID configured | 1. Open app root | One Tap prompt is initialized without breaking route rendering. | Manual | QA
TC-INV-001 | Inventory | List inventory | Critical | Functional | User is authenticated | 1. Open /inventory | Rows load in CustomDataGrid with server pagination and no console errors. | UI + API | QA
TC-INV-002 | Inventory | Create listing | Critical | Functional | User is on /inventory | 1. Open add modal 2. Fill required fields 3. Submit | Listing is created, success toast appears, list query is refreshed. | UI + API | QA
TC-INV-003 | Inventory | Edit listing | High | Functional | At least one listing exists | 1. Open edit modal for listing 2. Update fields 3. Save | Listing updates successfully and table reflects changes. | UI + API | QA
TC-INV-004 | Inventory | Delete listing | High | Functional | At least one listing exists | 1. Trigger delete action 2. Confirm in dialog | Listing is removed, success feedback shown, grid refreshes. | UI + API | QA
TC-ADV-001 | Advertisements | Create advertisement | High | Functional | User is on /advertisements | 1. Open add modal 2. Enter valid values 3. Submit | Advertisement record is created and visible in the ads list. | UI + API | QA
TC-ADV-002 | Advertisements | Advertisement details route | High | Functional | Advertisement exists | 1. Open /advertisements/:id | Detailed advertisement view loads with expected metadata. | UI + API | QA
TC-SUB-001 | Subscriptions | Create subscription | High | Functional | User is on /subscriptions | 1. Open add modal 2. Fill plan fields 3. Submit | Subscription is created, toast shown, and query cache invalidated. | UI + API | QA
TC-SUB-002 | Subscriptions | Edit subscription | High | Functional | Subscription exists | 1. Open edit modal 2. Change data 3. Save | Subscription updates without data loss and list shows updated values. | UI + API | QA
TC-USER-001 | User Management | Load users | High | Functional | User is authenticated | 1. Open /userManagement | User dataset loads and actions are available per row. | UI + API | QA
TC-USER-002 | User Management | Legacy sellers redirect | Medium | Functional | Authenticated session | 1. Open /sellers | Route redirects to /userManagement with no error. | UI | QA
TC-MSG-001 | Messages | Message thread load | High | Functional | Websocket/server available | 1. Open /messages | Messages page loads active conversations and unread counters. | UI + Integration | QA
TC-NOTIF-001 | Notifications | Notification list | Medium | Functional | Authenticated session | 1. Open /notifications | Notification list renders and shows accurate read/unread state. | UI + API | QA
TC-PROF-001 | Profile | Profile fetch | High | Functional | Authenticated session | 1. Open /profile | Current profile details are populated from API data. | UI + API | QA
TC-PROF-002 | Profile | Profile update | High | Functional | Profile page open | 1. Edit editable fields 2. Submit update | Profile updates successfully and success toast appears. | UI + API | QA
TC-TXN-001 | Transactions | Transaction list | High | Functional | Authenticated session | 1. Open /transactions | Transaction data loads with expected columns and formatting. | UI + API | QA
TC-DASH-001 | Dashboard | Metrics rendering | High | Functional | Authenticated session | 1. Open /dashboard | Stat cards/charts render with no crash and valid values. | UI + API | QA
TC-UX-001 | Theme | Theme toggle | Medium | Usability | Authenticated session | 1. Toggle theme in navigation | UI switches between light and dark themes consistently. | UI | QA
TC-ERR-001 | Routing | 404 page | Medium | Functional | None | 1. Navigate to unknown route, e.g., /abc123 | NotFound page is rendered. | UI | QA
TC-SEC-001 | API Security | JWT attached to requests | Critical | Security | User is logged in | 1. Trigger authenticated API request 2. Inspect headers | Authorization bearer token is added by axios interceptor. | API | QA + Dev
TC-SEC-002 | API Security | 401 handling | Critical | Security | Expired or invalid token | 1. Call protected endpoint | Session is handled gracefully (redirect and/or clear invalid auth state). | Integration | QA + Dev
TC-PERF-001 | Performance | Initial dashboard load | Medium | Performance | Warm backend | 1. Login 2. Measure dashboard fully loaded time | Dashboard interactive under agreed SLA threshold. | Manual + Monitoring | QA + DevOps
TC-RQ-001 | React Query | Mutation invalidates list query | High | Integration | List page open | 1. Create/update entity through modal 2. Observe grid refresh | Relevant query keys are invalidated and latest records are shown. | Integration | QA + Dev
TC-FORM-001 | Form Validation | Formik/Yup required fields | High | Negative | Open any create modal | 1. Leave required fields empty 2. Submit | Validation errors are shown and API is not called until form is valid. | UI | QA
TC-FORM-002 | Form Validation | SelectFieldWrapper options | Medium | Functional | Form includes category select | 1. Open select 2. Pick option from constants | Selected value is bound to Formik and submitted correctly. | UI | QA
TC-SKT-001 | Socket | Realtime updates | Medium | Integration | Socket server running | 1. Open messages/notifications 2. Trigger event from another user | Unread counts and views update without full-page refresh. | Integration | QA + Dev
TC-BUILD-001 | Build | Production build integrity | High | Release | Dependencies installed | 1. Run npm run build | Build completes without errors and outputs dist assets. | CI | DevOps

## Next Phase Deliverables
phase | stream | deliverable | rationale | priority | estimateWeeks | dependencies | successMetric
Phase 2 | Quality Engineering | Automated regression suite foundation | Protect critical admin workflows (auth, inventory, subscriptions, ads) from regressions. | P0 | 2 | Stable test environment + API seed data | At least 25 critical flows automated in CI with >95% pass rate.
Phase 2 | Observability | Client-side error tracking + release tagging | Faster diagnosis of production issues from SPA runtime and API failures. | P0 | 1 | Monitoring tool selection and DSN/env setup | Unhandled frontend exceptions captured with user/session context.
Phase 2 | Security | Auth/session hardening | Reduce risk from token misuse, stale sessions, and unauthorized route access. | P0 | 1 | Backend auth policy alignment | Security checklist signed off for JWT and route guard scenarios.
Phase 3 | User Management | Role-based permission matrix (RBAC) | Enable scoped access for support/admin/operator personas. | P1 | 2 | Backend claims/roles endpoints | All sensitive actions gated by role checks with audit-ready behavior.
Phase 3 | Messages & Notifications | Realtime reliability improvements | Improve message delivery confidence and unread count consistency. | P1 | 2 | Socket health endpoint and retry policy | Missed realtime updates reduced to near-zero in soak testing.
Phase 3 | Data Grid UX | Advanced filtering/export for major tables | Improve admin productivity for large datasets. | P1 | 2 | API support for filter/sort fields | Common support queries resolved without manual backend checks.
Phase 4 | Performance | Dashboard and listing performance optimization | Keep SPA responsive at scale as entities and activity grow. | P1 | 2 | Baseline profiling results | Dashboard interactive time reduced by at least 30% from baseline.
Phase 4 | Release Engineering | Preview environment + deployment quality gates | Catch release blockers before production and standardize sign-off. | P1 | 1 | CI/CD pipeline adjustments | All releases pass lint/build/smoke checks before production deploy.
Phase 4 | Analytics | Admin activity and business KPI instrumentation | Track usage outcomes and feature adoption across dashboard modules. | P2 | 2 | Analytics schema and event naming convention | KPI dashboard available for product and operations teams.

## Execution Plan
sprint | objective | keyOutputs | definitionOfDone
Sprint 1 | Stabilize quality baseline | Regression framework setup, smoke suite in CI, route/auth core coverage | CI runs on PR with pass/fail reporting and no flaky critical tests
Sprint 2 | Expand business-critical automation | Inventory, advertisements, subscriptions and transactions critical path coverage | Top-priority modules have passing regression checks and defect leakage reduced
Sprint 3 | Ship hardening and observability | Session-hardening updates, runtime error tracking, monitoring alerts | Security checks pass and production incidents are diagnosable within minutes
Sprint 4 | Prepare scale-oriented enhancements | RBAC implementation plan, data grid enhancements, performance backlog | Roadmap epic specs are implementation-ready with acceptance criteria

## Traceability
testCaseId | route | pageOrComponent | primaryService | queryOrState | riskArea
TC-AUTH-001 | /login | src/pages/auth/LoginUser.jsx | src/services/authService.js | JWT localStorage + PublicRoute | Authentication
TC-AUTH-004 | /dashboard | src/components/route/PrivateRoute.jsx | src/services/authService.js | Route guard session validation | Unauthorized access
TC-AUTH-005 | * | src/components/auth/GoogleOneTap.jsx | n/a | Google SDK prompt flow | SSO prompt reliability
TC-INV-001 | /inventory | src/pages/Inventory.jsx | src/services/listingService.js | TanStack Query listing fetch | Server pagination
TC-INV-002 | /inventory/add | src/components/modals/InventoryModal.jsx | src/services/listingService.js | Mutation + invalidateQueries | Create workflow
TC-ADV-001 | /advertisements/add | src/components/modals/ListingAdvModal.jsx | src/services/advertService.js | Mutation + list refresh | Ad publishing
TC-ADV-002 | /advertisements/:id | src/pages/AdvertisementDetails.jsx | src/services/advertService.js | Detail query (queryKey advert,id) | Detail rendering
TC-SUB-001 | /subscriptions/add | src/components/modals/SubscriptionModal.jsx | src/services/subscriptionService.js | Mutation + invalidateQueries | Subscription setup
TC-USER-001 | /userManagement | src/pages/UserManagement.jsx | src/services/authService.js | Grid state + filtering | User operations
TC-USER-002 | /sellers | src/App.jsx | n/a | Navigate redirect | Legacy route compatibility
TC-MSG-001 | /messages | src/pages/Messages.jsx | src/services/messageService.js | Query + socket events | Realtime unread consistency
TC-NOTIF-001 | /notifications | src/pages/Notifications.jsx | src/services/notificationService.js | Notification query + socket events | Read/unread accuracy
TC-PROF-001 | /profile | src/pages/Profile.jsx | src/services/queries.js | useUserProfileQuery | Profile data mapping
TC-PROF-002 | /profile | src/pages/Profile.jsx | src/services/sellerInfoService.js | Mutations + toast feedback | Profile updates
TC-TXN-001 | /transactions | src/pages/Transactions.jsx | n/a (currently local data) | Client state filter/search | Transaction presentation
TC-DASH-001 | /dashboard | src/pages/Dashboard.jsx | src/services/* | Metrics queries | Widget stability
TC-UX-001 | Global nav | src/components/navigations/Navigation.jsx | n/a | Theme mode toggle state | Visual consistency
TC-SEC-001 | All protected routes | src/api/axiosClient.js | src/api/axiosClient.js | Request interceptor | Auth header propagation
TC-RQ-001 | Inventory/Ads/Subscriptions | src/pages/* + src/components/modals/* | src/services/* | Query key invalidation behavior | Stale UI data
TC-BUILD-001 | n/a | package.json | Vite build pipeline | npm run build | Release readiness